## Dashboard
Franchise Development — Strategic Dashboard
EXECUTIVE LAYER · Live roll-up across all 1:1 trackers. Updated automatically — no duplicate data entry. (Open the file in Excel and allow recalculation for live values.)
14 |  | 9 |  | 1 |  | 1 | 1 |  | 38.14%
Active Projects |  | On Track |  | At Risk |  | Blocked | Complete |  | Avg % Complete
35 |  | 1 |  | 1 |  | 2 | 29 |  | 10
Total Active Tasks |  | Overdue Tasks |  | Due in 7 Days |  | Not Started | No Tasks Yet |  | Total People
Status by Focus Area | [6 empty] | Workload by Individual
Focus Area | Tasks | Complete | In Progress | Overdue | % Complete | Health | Person | Tasks | Open | Complete | Overdue | % Complete
1 – Unified Development System | 11 | 0 | 11 | 1 | 50% | R | Quick Chadwick | 10 | 8 | 2 | 0 | 41.5%
2 – Top-of-Funnel Lead Gen | 3 | 1 | 2 | 0 | 53.33% | G | MaryFran Anderson | 6 | 6 | 0 | 0 | 25%
3 – Broker Channel | 7 | 0 | 4 | 0 | 20% | R | Shane Mattingly | 7 | 7 | 0 | 1 | 27.14%
4 – Portfolio Brand Strategy | 2 | 0 | 2 | 0 | 25% | G | Leslie Toole | 1 | 1 | 0 | 0 | 50%
5 – Operational Infrastructure | 1 | 0 | 0 | 0 | 0% | Y | Leah Hanlon | 1 | 1 | 0 | 0 | 50%
6 – Automation & Content | 9 | 2 | 5 | 0 | 42.78% | G | Jamie Lavigne | 2 | 2 | 0 | 0 | 50%
7 – Operating Rhythm | 2 | 0 | 2 | 0 | 25% | G | Steve Griffith | 2 | 2 | 0 | 0 | 35%
8 – Talent Evaluation | 0 | 0 | 0 | 0 |  | - | Matt Motyka | 2 | 2 | 0 | 0 | 40%
[7 empty] | Alvaro Leal | 3 | 2 | 1 | 0 | 60%
[7 empty] | Cassidy Ford | 1 | 1 | 0 | 0 | 50%
Project Status Distribution
In Progress | 9
At Risk | 1
Blocked | 1
Complete | 1
Not Started | 2
No Tasks Yet | 29

## Strategic Plan
CGO - Strategic Plan
Plan includes 8 focus areas comprised of 44 total tactics to completion over the next 100 days.
1 | Build a Unified Franchise Development System |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary | Legend | Notes
|  | 1 | Implement standardized Mutual Evaluation Process (MEP) across all brands | P1-1 | Developers | Dobelbower | Short (90) | G | Current franchise development processes vary significantly by brand, creating inconsistent candidate experiences and reducing scalability. | na | not started
|  | 2 | Standardize pipeline stages, definitions, and reporting in CRM | P1-2 | Mattingly/Ruhlig | Dobelbower | Short (90) | G | Inconsistent pipeline definitions and reporting currently limit forecasting accuracy and portfolio-level visibility. | G | started & on track
|  | 3 | Implement DAP (Development Action Plan) timelines for all candidates | P1-3 | Developers | Dobelbower | Short (90) | G | Current candidate progression lacks consistent timelines and accountability, creating unnecessary delays and reduced closing certainty. | Y | resolving minor issues
|  | 4 | Standardize MTTD structure (confirmation event, not sales event) | P1-4 | Developers | Dobelbower | Mid (180) | na | MTTD execution varies significantly by brand and should function as a confirmation milestone rather than a late-stage persuasion event. | R | off track / needs attention
|  | 5 | Standardize lead qualification across brands (Lumin, SDR, etc.) | P1-5 | Mattingly/Ruhlig | Dobelbower | Short (90) | na | Qualification standards currently vary by brand, resulting in inconsistent lead quality and inefficient developer utilization.
|  | 6 | Launch weekly portfolio-wide pipeline call (eliminate silos) | P1-6 | Developers | Dobelbower | Short (90) | C | Weekly Pipeline Review kicked off 5/5
2 | Rebuild Top-of-Funnel Lead Generation |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Centralize non-broker marketing under Chadwick | P2-1 | Chadwick | Dobelbower | Short (90) | C | Non-broker lead generation efforts are currently fragmented across brands and lack centralized strategic prioritzation.
|  | 2 | Reallocate spend toward non-broker sourced channels | P2-2 | Thoma/Chadwick | Dobelbower | Short (90) | na | Marketing spend allocation is not consistently aligned with lead quality, conversion performance, or long-term scalability objectives.
|  | 3 | Build video-first funnel | P2-3 | M. Anderson/Leal | Dobelbower | Short (90) | G | Video and automation create an opportunity to improve candidate education, consistency, and developer scalability across all brands.
|  | 4 | Establish portfolio-level KPIs benchmarked against AFDR ratios | P2-4 | Mattingly | Dobelbower | Mid (180) | na | Portfolio-level KPIs are necessary to properly evaluate marketing efficiency, lead quality, and channel performance across brands.
|  | 5 | Eliminate low-quality lead sources | P2-5 | Chadwick | Dobelbower | Short (90) | na | Certain lead sources currently produce volume without corresponding conversion performance or franchisee quality.
3 | Optimize Broker Channel Performance |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Assign MaryFran as broker channel owner | P3-1 | MF. Anderson | Dobelbower | Short (90) | C | Broker relationships currently lack centralized ownership and consistent management across the portfolio.
|  | 2 | Route 100% of broker leads through CRM for centralized intake and visibility. | P3-2 | Mattingly | Dobelbower | Short (90) | G | Shared inboxes and inconsistent lead routing create missed opportunities and limited visibility into broker activity.
|  | 3 | Implement rules-based lead distribution | P3-3 | Mattingly/Ruhlig | Dobelbower | Short (90) | na | Lead distribution should prioritize fairness, responsiveness, and performance while eliminating perception of uneven opportunity.
|  | 4 | Enforce speed-to-lead SLAs | P3-4 | MF. Anderson | Dobelbower | Short (90) | na | Response speed remains one of the largest drivers of broker lead conversion and candidate engagement.
|  | 5 | Segment Brokers into Tier 1/Tier 2/ Tier 3 | P3-5 | MF. Anderson | Dobelbower |  | na | Not all broker relationships generate equal value, requiring prioritization based on production and lead quality.
|  | 6 | Introduce performance-based lead weighting | P3-6 | Mattingly/Ruhlig | Dobelbower |  | na | Lead distribution should reward execution and conversion performance while maintaining equitable opportunity across the team.
|  | 7 | Build weekly broker channel performance reporting | P3-7 | Mattingly/Ruhlig | Dobelbower | Short (90) | na | Broker performance visibility is currently limited, making it difficult to optimize relationships and conversion performance.
4 | Execute Portfolio-Based Brand Strategy |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Position The Seals as a low-cost, high-whitespace growth brand | P4-1 | Anderson/Chadwick | Dobelbower | Short (90) | G | The Seals presents an opportunity for accelerated unit growth due to low investment requirements, recurring revenue characteristics, and significant whitespace availability.
|  | 2 | Position 1-Tom as a flagship growth brand | P4-2 | Anderson/Chadwick | Dobelbower | Short (90) | G | 1-Tom possesses strong branding, broad market appeal, and favorable long-term scalability characteristics.
|  | 3 | Align Kitchen Guard growth strategy with Strategic Accounts initiatives | P4-3 | Hatcher | Dobelbower | Long (270) | G | Kitchen Guard’s compliance-driven recurring revenue model aligns well with enterprise and Strategic Account positioning opportunities.
|  | 4 | Reposition Prism as a multi-service platform opportunity | P4-4 | Anderson/Chadwick | Dobelbower | Short (90) | G | Prism’s multi-service structure creates an opportunity to increase average deal size and long-term franchisee value.
|  | 5 | Maintain stable, quality-focused growth for U.S. Lawns | P4-5 | Steeves | Dobelbower | Short (90) | G | U.S. Lawns serves as a mature and stable portfolio brand with strong recognition and operational consistency.
|  | 6 | Utilize Clintar as a selective strategic growth vehicle | P4-6 | Motyka | Dobelbower | Mid (180) | G | Clintar should be positioned toward experienced operators and strategic opportunities rather than high-volume franchise sales efforts.
|  | 7 | Rebuild validation and franchisee confidence within MilliCare | P4-7 | Griffith/Weaver | Dobelbower | Long (270) | na | Long-term MilliCare growth requires improvement in franchisee sentiment, validation consistency, and economic confidence.
5 | Strengthen Operational Infrastructure & Visbility |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Replace shared territory check inboxes with CRM routing | P5-1 | Mattingly | Dobelbower | Short (90) | na | Shared territory check workflows currently create operational inefficiencies and inconsistent response times.
|  | 2 | Implement territory check response SLA | P5-2 | MF. Anderson | Dobelbower | Short (90) | G | Fast and consistent response times are critical to broker experience and franchise sales momentum.
|  | 3 | Standardize lead assignment and routing logic | P5-3 | Mattingly | Dobelbower | Short (90) | na | Lead routing should prioritize transparency, accountability, and operational consistency across brands.
|  | 4 | Build centralized KPI dashboard and reporting visibility | P5-4 | Mattingly/Ruhlig | Dobelbower | Mid (180) | na | Leadership currently lacks consistent portfolio-wide visibility into funnel health and conversion trends.
|  | 5 | Improve CRM adoption and reporting discipline | P5-5 | Developers | Dobelbower/Mattingly | Short (90) | G | Consistent CRM usage is required to improve forecasting accuracy and operational visibility.
| Leverage Automation & Content to Improve Scalability |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
6 |  | 1 | Develop standardized brand overview videos | P6-1 | M Anderson/Leal | Dobelbower | Mid (180) | G | Standardized brand messaging improves candidate consistency and reduces repetitive developer workload.
|  | 2 | Develop validation preparation and candidate education content | P6-2 | Dobelbower | N/A | Short (90) | G | Better-prepared candidates improve validation outcomes and increase overall process efficiency.
|  | 3 | Create standardized FDD and process walkthrough videos | P6-3 | M Anderson/Leal | Dobelbower | Short (90) | na | Automation of repetitive educational content increases scalability and developer capacity.
|  | 4 | Build centralized content library across brands | P6-4 | M Anderson/Leal | Dobelbower | Long (270) | G | Centralized content infrastructure improves consistency and speed of deployment across the portfolio.
|  | 6 | Automate early-stage candidate education | P6-5 | Mattingly/Ruhlig | Dobelbower | Mid (180) | G | Automation creates operational leverage while improving consistency of the candidate experience.
7 | Establish Operating Rhythm & Accountability |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Implement weekly KPI scorecards by brand, developer, and source | P7-1 | Mattingly | Dobelbower | Mid (180) | G | Transparent performance reporting improves visibility and operational decision-making.
|  | 2 | Conduct monthly funnel conversion and marketing reviews | P7-2 | Chadwick/MF Anderson | Dobelbower | Short (90) | G | Regular conversion analysis is necessary to optimize marketing efficiency and franchise development performance.
|  | 3 | Standardize forecasting methodology | P7-3 | Mattingly | Dobelbower | Short (90) | G | Forecasting methodologies currently vary across brands, limiting portfolio-level planning and visibility.
|  | 4 | Establish clear initiative ownership and accountability | P7-4 | Dobelbower | N/A | Short (90) | G | Consistent ownership structures are required to improve execution discipline and cross-functional alignment.
8 | Talent Evaluation |  |  | Proj ID | Lead | Other | Timing | Status | Notes / Commentary
|  | 1 | Evaluate the current Franchise Development team to identify top performers, growth opportunities, and long-term leadership potential. | P8-1 | Dobelbower | N/A | Short (90) | G | This assessment will help ensure the organization has the right talent structure in place to support scalable growth across all brands.
|  | 2 | Establish standardized performance expectations and KPI accountability across all Franchise Development roles. | P8-2 | Dobelbower | N/A | Short (90) | G | Creating consistent scorecards and benchmarks will improve visibility, alignment, and operational discipline throughout the department.
|  | 3 | Identify capability gaps and organizational needs across recruiting, sales execution, broker management, and lead conversion. | P8-3 | Dobelbower | N/A | Short (90) | G | Understanding where additional support, training, or restructuring is needed will strengthen overall development effectiveness.
|  | 4 | Build a long-term talent development strategy focused on coaching, succession planning, and cross-brand collaboration. | P8-4 | Dobelbower | N/A | Short (90) | G | Investing in team development will create a more scalable and sustainable franchise development organization over time.

## Projects
Projects — Tactic Roll-Up (auto)
AGGREGATION LAYER · One row per tactic. Status, %, risks and milestones roll up automatically from the 1:1 tabs. Run project reviews here or open the Project Review tab.
Project ID | Focus Area | Project / Tactic Name | Exec Owner | Lead Owner | Strategic Goal (why) | Timing | Tasks | Current Status | % Complete | Overdue | Blocked | Key Risks | Next Milestone | Health | Review
P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Dobelbower | Developers | Current franchise development processes vary significantly by brand, creating inconsistent candidate experiences and reducing scalability. | Short (90) | 10 | In Progress | 50% | 0 | 0 | On track |  | G | Open | 0 | 10 | 0
P1-2 | 1 – Unified Development System | Standardize pipeline stages, definitions, and reporting in CRM | Dobelbower | Mattingly/Ruhlig | Inconsistent pipeline definitions and reporting currently limit forecasting accuracy and portfolio-level visibility. | Short (90) | 1 | At Risk | 50% | 1 | 0 | 1 overdue task(s) |  | R | Open | 0 | 1 | 0
P1-3 | 1 – Unified Development System | Implement DAP (Development Action Plan) timelines for all candidates | Dobelbower | Developers | Current candidate progression lacks consistent timelines and accountability, creating unnecessary delays and reduced closing certainty. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P1-4 | 1 – Unified Development System | Standardize MTTD structure (confirmation event, not sales event) | Dobelbower | Developers | MTTD execution varies significantly by brand and should function as a confirmation milestone rather than a late-stage persuasion event. | Mid (180) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P1-5 | 1 – Unified Development System | Standardize lead qualification across brands (Lumin, SDR, etc.) | Dobelbower | Mattingly/Ruhlig | Qualification standards currently vary by brand, resulting in inconsistent lead quality and inefficient developer utilization. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P1-6 | 1 – Unified Development System | Launch weekly portfolio-wide pipeline call (eliminate silos) | Dobelbower | Developers | Weekly Pipeline Review kicked off 5/5 | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P2-1 | 2 – Top-of-Funnel Lead Gen | Centralize non-broker marketing under Chadwick | Dobelbower | Chadwick | Non-broker lead generation efforts are currently fragmented across brands and lack centralized strategic prioritzation. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P2-2 | 2 – Top-of-Funnel Lead Gen | Reallocate spend toward non-broker sourced channels | Dobelbower | Thoma/Chadwick | Marketing spend allocation is not consistently aligned with lead quality, conversion performance, or long-term scalability objectives. | Short (90) | 1 | Complete | 100% | 0 | 0 | On track |  | G | Open | 1 | 0 | 0
P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Dobelbower | M. Anderson/Leal | Video and automation create an opportunity to improve candidate education, consistency, and developer scalability across all brands. | Short (90) | 2 | In Progress | 30% | 0 | 0 | On track |  | G | Open | 0 | 2 | 0
P2-4 | 2 – Top-of-Funnel Lead Gen | Establish portfolio-level KPIs benchmarked against AFDR ratios | Dobelbower | Mattingly | Portfolio-level KPIs are necessary to properly evaluate marketing efficiency, lead quality, and channel performance across brands. | Mid (180) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P2-5 | 2 – Top-of-Funnel Lead Gen | Eliminate low-quality lead sources | Dobelbower | Chadwick | Certain lead sources currently produce volume without corresponding conversion performance or franchisee quality. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | Dobelbower | MF. Anderson | Broker relationships currently lack centralized ownership and consistent management across the portfolio. | Short (90) | 3 | Blocked | 13% | 0 | 1 | 1 blocked / 0 overdue |  | R | Open | 0 | 1 | 1
P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | Dobelbower | Mattingly | Shared inboxes and inconsistent lead routing create missed opportunities and limited visibility into broker activity. | Short (90) | 2 | In Progress | 40% | 0 | 0 | On track |  | G | Open | 0 | 2 | 0
P3-3 | 3 – Broker Channel | Implement rules-based lead distribution | Dobelbower | Mattingly/Ruhlig | Lead distribution should prioritize fairness, responsiveness, and performance while eliminating perception of uneven opportunity. | Short (90) | 1 | Not Started | 0% | 0 | 0 | On track |  | Y | Open | 0 | 0 | 0
P3-4 | 3 – Broker Channel | Enforce speed-to-lead SLAs | Dobelbower | MF. Anderson | Response speed remains one of the largest drivers of broker lead conversion and candidate engagement. | Short (90) | 1 | In Progress | 20% | 0 | 0 | On track |  | G | Open | 0 | 1 | 0
P3-5 | 3 – Broker Channel | Segment Brokers into Tier 1/Tier 2/ Tier 3 | Dobelbower | MF. Anderson | Not all broker relationships generate equal value, requiring prioritization based on production and lead quality. |  | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P3-6 | 3 – Broker Channel | Introduce performance-based lead weighting | Dobelbower | Mattingly/Ruhlig | Lead distribution should reward execution and conversion performance while maintaining equitable opportunity across the team. |  | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P3-7 | 3 – Broker Channel | Build weekly broker channel performance reporting | Dobelbower | Mattingly/Ruhlig | Broker performance visibility is currently limited, making it difficult to optimize relationships and conversion performance. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-1 | 4 – Portfolio Brand Strategy | Position The Seals as a low-cost, high-whitespace growth brand | Dobelbower | Anderson/Chadwick | The Seals presents an opportunity for accelerated unit growth due to low investment requirements, recurring revenue characteristics, and significant whitespace availability. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-2 | 4 – Portfolio Brand Strategy | Position 1-Tom as a flagship growth brand | Dobelbower | Anderson/Chadwick | 1-Tom possesses strong branding, broad market appeal, and favorable long-term scalability characteristics. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-3 | 4 – Portfolio Brand Strategy | Align Kitchen Guard growth strategy with Strategic Accounts initiatives | Dobelbower | Hatcher | Kitchen Guard’s compliance-driven recurring revenue model aligns well with enterprise and Strategic Account positioning opportunities. | Long (270) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-4 | 4 – Portfolio Brand Strategy | Reposition Prism as a multi-service platform opportunity | Dobelbower | Anderson/Chadwick | Prism’s multi-service structure creates an opportunity to increase average deal size and long-term franchisee value. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-5 | 4 – Portfolio Brand Strategy | Maintain stable, quality-focused growth for U.S. Lawns | Dobelbower | Steeves | U.S. Lawns serves as a mature and stable portfolio brand with strong recognition and operational consistency. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P4-6 | 4 – Portfolio Brand Strategy | Utilize Clintar as a selective strategic growth vehicle | Dobelbower | Motyka | Clintar should be positioned toward experienced operators and strategic opportunities rather than high-volume franchise sales efforts. | Mid (180) | 1 | In Progress | 30% | 0 | 0 | On track |  | G | Open | 0 | 1 | 0
P4-7 | 4 – Portfolio Brand Strategy | Rebuild validation and franchisee confidence within MilliCare | Dobelbower | Griffith/Weaver | Long-term MilliCare growth requires improvement in franchisee sentiment, validation consistency, and economic confidence. | Long (270) | 1 | In Progress | 20% | 0 | 0 | 1 roadblock(s) flagged |  | G | Open | 0 | 1 | 1
P5-1 | 5 – Operational Infrastructure | Replace shared territory check inboxes with CRM routing | Dobelbower | Mattingly | Shared territory check workflows currently create operational inefficiencies and inconsistent response times. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P5-2 | 5 – Operational Infrastructure | Implement territory check response SLA | Dobelbower | MF. Anderson | Fast and consistent response times are critical to broker experience and franchise sales momentum. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P5-3 | 5 – Operational Infrastructure | Standardize lead assignment and routing logic | Dobelbower | Mattingly | Lead routing should prioritize transparency, accountability, and operational consistency across brands. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P5-4 | 5 – Operational Infrastructure | Build centralized KPI dashboard and reporting visibility | Dobelbower | Mattingly/Ruhlig | Leadership currently lacks consistent portfolio-wide visibility into funnel health and conversion trends. | Mid (180) | 1 | Not Started | 0% | 0 | 0 | On track |  | Y | Open | 0 | 0 | 0
P5-5 | 5 – Operational Infrastructure | Improve CRM adoption and reporting discipline | Dobelbower/Mattingly | Developers | Consistent CRM usage is required to improve forecasting accuracy and operational visibility. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Dobelbower | M Anderson/Leal | Standardized brand messaging improves candidate consistency and reduces repetitive developer workload. | Mid (180) | 9 | In Progress | 43% | 0 | 0 | On track |  | G | Open | 2 | 5 | 0
P6-2 | 6 – Automation & Content | Develop validation preparation and candidate education content | N/A | Dobelbower | Better-prepared candidates improve validation outcomes and increase overall process efficiency. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P6-3 | 6 – Automation & Content | Create standardized FDD and process walkthrough videos | Dobelbower | M Anderson/Leal | Automation of repetitive educational content increases scalability and developer capacity. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P6-4 | 6 – Automation & Content | Build centralized content library across brands | Dobelbower | M Anderson/Leal | Centralized content infrastructure improves consistency and speed of deployment across the portfolio. | Long (270) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P6-5 | 6 – Automation & Content | Automate early-stage candidate education | Dobelbower | Mattingly/Ruhlig | Automation creates operational leverage while improving consistency of the candidate experience. | Mid (180) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P7-1 | 7 – Operating Rhythm | Implement weekly KPI scorecards by brand, developer, and source | Dobelbower | Mattingly | Transparent performance reporting improves visibility and operational decision-making. | Mid (180) | 1 | In Progress | 30% | 0 | 0 | On track |  | G | Open | 0 | 1 | 0
P7-2 | 7 – Operating Rhythm | Conduct monthly funnel conversion and marketing reviews | Dobelbower | Chadwick/MF Anderson | Regular conversion analysis is necessary to optimize marketing efficiency and franchise development performance. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P7-3 | 7 – Operating Rhythm | Standardize forecasting methodology | Dobelbower | Mattingly | Forecasting methodologies currently vary across brands, limiting portfolio-level planning and visibility. | Short (90) | 1 | In Progress | 20% | 0 | 0 | On track |  | G | Open | 0 | 1 | 0
P7-4 | 7 – Operating Rhythm | Establish clear initiative ownership and accountability | N/A | Dobelbower | Consistent ownership structures are required to improve execution discipline and cross-functional alignment. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P8-1 | 8 – Talent Evaluation | Evaluate the current Franchise Development team to identify top performers, growth opportunities, and long-term leadership potential. | N/A | Dobelbower | This assessment will help ensure the organization has the right talent structure in place to support scalable growth across all brands. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P8-2 | 8 – Talent Evaluation | Establish standardized performance expectations and KPI accountability across all Franchise Development roles. | N/A | Dobelbower | Creating consistent scorecards and benchmarks will improve visibility, alignment, and operational discipline throughout the department. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P8-3 | 8 – Talent Evaluation | Identify capability gaps and organizational needs across recruiting, sales execution, broker management, and lead conversion. | N/A | Dobelbower | Understanding where additional support, training, or restructuring is needed will strengthen overall development effectiveness. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
P8-4 | 8 – Talent Evaluation | Build a long-term talent development strategy focused on coaching, succession planning, and cross-brand collaboration. | N/A | Dobelbower | Investing in team development will create a more scalable and sustainable franchise development organization over time. | Short (90) | 0 | No Tasks Yet |  | 0 | 0 |  |  |  | Open | 0 | 0 | 0
Formulas:
Next Milestone = IFERROR(minifs('All Tasks'!$L2:L404,'All Tasks'!$B2:B404,[Project ID],'All Tasks'!$I2:I404,"<>Complete",'All Tasks'!$L2:L404,">"&(TODAY()-1)),"")

## Project Review
Project Review
Pick a Project ID — the header and the full task list (everyone working on that tactic) populate automatically.
Select Project ID > | P1-1
Project / Tactic Name | Implement standardized Mutual Evaluation Process (MEP) across all brands
Focus Area | 1 – Unified Development System
Executive Owner | Dobelbower
Lead Owner | Developers
Timing | Short (90)
Strategic Goal (why) | Current franchise development processes vary significantly by brand, creating inconsistent candidate experiences and reducing scalability.
Current Status | In Progress
% Complete | 50%
Overdue Tasks | 0
Blocked Tasks | 0
Key Risks | On track
Next Milestone
Tasks for this Project (everyone working on the tactic)
Task ID | Assigned To | Task Description | Role | Priority | Status | % Comp | Start | Due | Days Left | Roadblock | Last Update | Next Step

## All Tasks
All Tasks — Consolidated Feed (auto)
ENGINE · Every task from every 1:1 tab is pulled here automatically. Do not type here — update tasks on the individual tabs. Filter by Project ID or Assigned To for any view.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Source Tab | Overdue | Due7d | DaysToDue | EffPct | HasRoad | Active
QC-001 | P2-2 | 2 – Top-of-Funnel Lead Gen | Reallocate spend toward non-broker sourced channels | Quick Chadwick | Owner | Develop Marketing Spend Reallocation Plan | High | Complete | 100% | 2026-05-05 | 2026-05-22 | 0 | 0 | Reviewed plan; edits suggested & incorporated | Monitor reallocated spend vs broker channels | Quick Chadwick | 0 | 0 | -6 | 100% | 0 | 1
QC-002 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Quick Chadwick | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Quick Chadwick | 0 | 0 | 16 | 50% | 0 | 1
QC-003 | P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Quick Chadwick | Owner | Video Coordination with Madsen Anderson | High | In Progress | 30% | 2026-05-15 | 2026-06-20 | 0 | 0 | Coordinating shoot schedule | Lock production calendar | Quick Chadwick | 0 | 0 | 23 | 30% | 0 | 1
QC-004 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – 1-Tom) | High | Complete | 100% | 2026-05-01 | 2026-05-20 | 0 | 0 | Completed | Publish to content library | Quick Chadwick | 0 | 0 | -8 | 100% | 0 | 1
QC-005 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – The Seals) | Medium | In Progress | 40% | 2026-05-10 | 2026-06-30 | 0 | 0 | JL has sample; could be used as sub | Confirm sub footage with Jamie | Quick Chadwick | 0 | 0 | 33 | 40% | 0 | 1
QC-006 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Kitchen Guard) | Medium | In Progress | 25% | 2026-05-10 | 2026-07-15 | 0 | 0 | Could use Bytes & Insights for sub | Source sub footage | Quick Chadwick | 0 | 0 | 48 | 25% | 0 | 1
QC-007 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – MilliCare) | Medium | Not Started | 0% | 2026-06-01 | 2026-07-31 | Coordinate with Steve Griffith | 0 | 0 | Kickoff with SG | Quick Chadwick | 0 | 0 | 64 | 0% | 0 | 1
QC-008 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Prism) | Medium | In Progress | 40% | 2026-05-10 | 2026-06-30 | 0 | 0 | JL has sample | Confirm sub footage | Quick Chadwick | 0 | 0 | 33 | 40% | 0 | 1
QC-009 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Clintar) | Medium | In Progress | 30% | 2026-05-10 | 2026-07-15 | 0 | 0 | Could use TES for sub | Source sub footage | Quick Chadwick | 0 | 0 | 48 | 30% | 0 | 1
QC-010 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – US Lawns) | Medium | Not Started | 0% | 2026-06-01 | 2026-07-31 | Coordinate with JS | 0 | 0 | Kickoff with JS | Quick Chadwick | 0 | 0 | 64 | 0% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
MFA-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | MaryFran Anderson | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | MaryFran Anderson | 0 | 0 | 16 | 50% | 0 | 1
MFA-002 | P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | MaryFran Anderson | Owner | Broker Portal Update | High | In Progress | 40% | 2026-05-12 | 2026-06-03 | 0 | 0 | Updating broker portal records | Finalize portal field mapping | MaryFran Anderson | 0 | 1 | 6 | 40% | 0 | 1
MFA-003 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | Broker Engagement Opportunities (membership opps) | Medium | In Progress | 30% | 2026-05-12 | 2026-06-15 | 0 | 0 | Coordinating with Chadwick | Identify missed membership opportunities | MaryFran Anderson | 0 | 0 | 18 | 30% | 0 | 1
MFA-004 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | Broker Outreach Campaign (HubSpot drip build) | High | Blocked | 10% | 2026-06-01 | 2026-06-27 | HubSpot drip assets from QC | Waiting on HubSpot drip assets from Chadwick | Coordinate with QC | Unblock drip assets, then define sequence | MaryFran Anderson | 0 | 0 | 30 | 10% | 1 | 1
MFA-005 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | In-Person Broker D-Day Event Planning | Medium | Not Started | 0% | 2026-06-15 | 2026-08-15 | 0 | 0 | Not started | Draft event concept & budget | MaryFran Anderson | 0 | 0 | 79 | 0% | 0 | 1
MFA-006 | P3-4 | 3 – Broker Channel | Enforce speed-to-lead SLAs | MaryFran Anderson | Owner | Enforce speed-to-lead SLAs | High | In Progress | 20% | 2026-05-20 | 2026-06-20 | 0 | 0 | Defining SLA thresholds | Publish SLA standard to broker team | MaryFran Anderson | 0 | 0 | 23 | 20% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
SM-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Shane Mattingly | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Shane Mattingly | 0 | 0 | 16 | 50% | 0 | 1
SM-002 | P1-2 | 1 – Unified Development System | Standardize pipeline stages, definitions, and reporting in CRM | Shane Mattingly | Owner | Standardize pipeline stages, definitions & reporting in CRM | Critical | In Progress | 50% | 2026-05-01 | 2026-05-26 | 0 | 0 | Draft stage definitions circulated | Finalize stage definitions & lock CRM config | Shane Mattingly | 1 | 0 | -2 | 50% | 0 | 1
SM-003 | P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | Shane Mattingly | Owner | Route 100% of broker leads through CRM | High | In Progress | 40% | 2026-05-05 | 2026-06-20 | Broker portal update (MFA) | 0 | Building intake routing | Test routing with sample broker leads | Shane Mattingly | 0 | 0 | 23 | 40% | 0 | 1
SM-004 | P5-4 | 5 – Operational Infrastructure | Build centralized KPI dashboard and reporting visibility | Shane Mattingly | Owner | Build centralized KPI dashboard & reporting visibility | Critical | Not Started | 0% | 2026-06-01 | 2026-07-18 | Pipeline stage standardization (P1-2) | 0 | Pending stage standardization | Spec dashboard KPIs | Shane Mattingly | 0 | 0 | 51 | 0% | 0 | 1
SM-005 | P7-1 | 7 – Operating Rhythm | Implement weekly KPI scorecards by brand, developer, and source | Shane Mattingly | Owner | Implement weekly KPI scorecards by brand, developer & source | High | In Progress | 30% | 2026-05-10 | 2026-06-27 | 0 | 0 | Scorecard v1 drafted | Automate weekly refresh | Shane Mattingly | 0 | 0 | 30 | 30% | 0 | 1
SM-006 | P7-3 | 7 – Operating Rhythm | Standardize forecasting methodology | Shane Mattingly | Owner | Standardize forecasting methodology | High | In Progress | 20% | 2026-05-15 | 2026-07-03 | 0 | 0 | Reviewing brand forecast inputs | Align methodology across brands | Shane Mattingly | 0 | 0 | 36 | 20% | 0 | 1
SM-007 | P3-3 | 3 – Broker Channel | Implement rules-based lead distribution | Shane Mattingly | Owner | Implement rules-based lead distribution | Medium | Not Started | 0% | 2026-06-10 | 2026-07-25 | 0 | 0 | Not started | Define distribution rules | Shane Mattingly | 0 | 0 | 58 | 0% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
LT-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Leslie Toole | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Leslie Toole | 0 | 0 | 16 | 50% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
LH-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Leah Hanlon | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Leah Hanlon | 0 | 0 | 16 | 50% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
JL-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Jamie Lavigne | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Jamie Lavigne | 0 | 0 | 16 | 50% | 0 | 1
JL-002 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Jamie Lavigne | Support | Provide Signature 7 sample / sub footage | Low | In Progress | 50% | 2026-05-10 | 2026-06-20 | 0 | 0 | Sample available for The Seals & Prism | Share footage with Chadwick | Jamie Lavigne | 0 | 0 | 23 | 50% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
SG-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Steve Griffith | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Steve Griffith | 0 | 0 | 16 | 50% | 0 | 1
SG-002 | P4-7 | 4 – Portfolio Brand Strategy | Rebuild validation and franchisee confidence within MilliCare | Steve Griffith | Owner | Rebuild validation & franchisee confidence within MilliCare | High | In Progress | 20% | 2026-05-10 | 2026-09-30 | 0 | Franchisee sentiment low; validation inconsistent | Mapping current validators | Build validator readiness plan | Steve Griffith | 0 | 0 | 125 | 20% | 1 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
MM-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Matt Motyka | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Matt Motyka | 0 | 0 | 16 | 50% | 0 | 1
MM-002 | P4-6 | 4 – Portfolio Brand Strategy | Utilize Clintar as a selective strategic growth vehicle | Matt Motyka | Owner | Position Clintar as a selective strategic growth vehicle | Medium | In Progress | 30% | 2026-05-10 | 2026-08-15 | 0 | 0 | Defining target operator profile | Draft selective growth criteria | Matt Motyka | 0 | 0 | 79 | 30% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
AL-001 | P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Alvaro Leal | Contributor | Video Coordination with Madsen Anderson | High | In Progress | 30% | 2026-05-15 | 2026-06-20 | 0 | 0 | Coordinating with Chadwick | Align on shot list | Alvaro Leal | 0 | 0 | 23 | 30% | 0 | 1
AL-002 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Alvaro Leal | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Alvaro Leal | 0 | 0 | 16 | 50% | 0 | 1
AL-003 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Alvaro Leal | Owner | Video Project (Signature 7 – 1-Tom) | High | Complete | 100% | 2026-05-01 | 2026-05-20 | 0 | 0 | Complete | Hand off final cut to library | Alvaro Leal | 0 | 0 | -8 | 100% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
CF-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Cassidy Ford | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 | 0 | 0 | Assigned 5/20 | Complete sections 2-3 | Cassidy Ford | 0 | 0 | 16 | 50% | 0 | 1
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
[17 empty] | 0 | 0 |  |  | 0 | 0
Formulas:
Start Date = IF('Quick Chadwick'!$[Project ID]="","",'Quick Chadwick'!$[Start Date])
Due Date = IF('Quick Chadwick'!$[Project ID]="","",'Quick Chadwick'!$[Due Date])
Overdue = IF(OR([Project ID]="",[Status]="Complete",[Due Date]=""),0,IF([Due Date]<TODAY(),1,0))
Due7d = IF(OR([Project ID]="",[Status]="Complete",[Due Date]=""),0,IF(AND([Due Date]>=TODAY(),[Due Date]<=TODAY()+7),1,0))
DaysToDue = IF(OR([Project ID]="",[Due Date]=""),"",[Due Date]-TODAY())
Last Update = IF('Quick Chadwick'!$[Project ID]="","",'Quick Chadwick'!$[Last Update])

## Quick Chadwick
Quick Chadwick — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
QC-001 | P2-2 | 2 – Top-of-Funnel Lead Gen | Reallocate spend toward non-broker sourced channels | Quick Chadwick | Owner | Develop Marketing Spend Reallocation Plan | High | Complete | 100% | 2026-05-05 | 2026-05-22 |  |  | Reviewed plan; edits suggested & incorporated | Monitor reallocated spend vs broker channels | Open Project
QC-002 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Quick Chadwick | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
QC-003 | P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Quick Chadwick | Owner | Video Coordination with Madsen Anderson | High | In Progress | 30% | 2026-05-15 | 2026-06-20 |  |  | Coordinating shoot schedule | Lock production calendar | Open Project
QC-004 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – 1-Tom) | High | Complete | 100% | 2026-05-01 | 2026-05-20 |  |  | Completed | Publish to content library | Open Project
QC-005 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – The Seals) | Medium | In Progress | 40% | 2026-05-10 | 2026-06-30 |  |  | JL has sample; could be used as sub | Confirm sub footage with Jamie | Open Project
QC-006 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Kitchen Guard) | Medium | In Progress | 25% | 2026-05-10 | 2026-07-15 |  |  | Could use Bytes & Insights for sub | Source sub footage | Open Project
QC-007 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – MilliCare) | Medium | Not Started | 0% | 2026-06-01 | 2026-07-31 | Coordinate with Steve Griffith |  |  | Kickoff with SG | Open Project
QC-008 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Prism) | Medium | In Progress | 40% | 2026-05-10 | 2026-06-30 |  |  | JL has sample | Confirm sub footage | Open Project
QC-009 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – Clintar) | Medium | In Progress | 30% | 2026-05-10 | 2026-07-15 |  |  | Could use TES for sub | Source sub footage | Open Project
QC-010 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Quick Chadwick | Owner | Video Project (Signature 7 – US Lawns) | Medium | Not Started | 0% | 2026-06-01 | 2026-07-31 | Coordinate with JS |  |  | Kickoff with JS | Open Project

## MaryFran Anderson
MaryFran Anderson — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
MFA-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | MaryFran Anderson | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
MFA-002 | P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | MaryFran Anderson | Owner | Broker Portal Update | High | In Progress | 40% | 2026-05-12 | 2026-06-03 |  |  | Updating broker portal records | Finalize portal field mapping | Open Project
MFA-003 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | Broker Engagement Opportunities (membership opps) | Medium | In Progress | 30% | 2026-05-12 | 2026-06-15 |  |  | Coordinating with Chadwick | Identify missed membership opportunities | Open Project
MFA-004 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | Broker Outreach Campaign (HubSpot drip build) | High | Blocked | 10% | 2026-06-01 | 2026-06-27 | HubSpot drip assets from QC | Waiting on HubSpot drip assets from Chadwick | Coordinate with QC | Unblock drip assets, then define sequence | Open Project
MFA-005 | P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | MaryFran Anderson | Owner | In-Person Broker D-Day Event Planning | Medium | Not Started | 0% | 2026-06-15 | 2026-08-15 |  |  | Not started | Draft event concept & budget | Open Project
MFA-006 | P3-4 | 3 – Broker Channel | Enforce speed-to-lead SLAs | MaryFran Anderson | Owner | Enforce speed-to-lead SLAs | High | In Progress | 20% | 2026-05-20 | 2026-06-20 |  |  | Defining SLA thresholds | Publish SLA standard to broker team | Open Project

## Shane Mattingly
Shane Mattingly — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
SM-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Shane Mattingly | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
SM-002 | P1-2 | 1 – Unified Development System | Standardize pipeline stages, definitions, and reporting in CRM | Shane Mattingly | Owner | Standardize pipeline stages, definitions & reporting in CRM | Critical | In Progress | 50% | 2026-05-01 | 2026-05-26 |  |  | Draft stage definitions circulated | Finalize stage definitions & lock CRM config | Open Project
SM-003 | P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | Shane Mattingly | Owner | Route 100% of broker leads through CRM | High | In Progress | 40% | 2026-05-05 | 2026-06-20 | Broker portal update (MFA) |  | Building intake routing | Test routing with sample broker leads | Open Project
SM-004 | P5-4 | 5 – Operational Infrastructure | Build centralized KPI dashboard and reporting visibility | Shane Mattingly | Owner | Build centralized KPI dashboard & reporting visibility | Critical | Not Started | 0% | 2026-06-01 | 2026-07-18 | Pipeline stage standardization (P1-2) |  | Pending stage standardization | Spec dashboard KPIs | Open Project
SM-005 | P7-1 | 7 – Operating Rhythm | Implement weekly KPI scorecards by brand, developer, and source | Shane Mattingly | Owner | Implement weekly KPI scorecards by brand, developer & source | High | In Progress | 30% | 2026-05-10 | 2026-06-27 |  |  | Scorecard v1 drafted | Automate weekly refresh | Open Project
SM-006 | P7-3 | 7 – Operating Rhythm | Standardize forecasting methodology | Shane Mattingly | Owner | Standardize forecasting methodology | High | In Progress | 20% | 2026-05-15 | 2026-07-03 |  |  | Reviewing brand forecast inputs | Align methodology across brands | Open Project
SM-007 | P3-3 | 3 – Broker Channel | Implement rules-based lead distribution | Shane Mattingly | Owner | Implement rules-based lead distribution | Medium | Not Started | 0% | 2026-06-10 | 2026-07-25 |  |  | Not started | Define distribution rules | Open Project

## Leslie Toole
Leslie Toole — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
LT-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Leslie Toole | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project

## Leah Hanlon
Leah Hanlon — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
LH-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Leah Hanlon | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project

## Jamie Lavigne
Jamie Lavigne — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
JL-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Jamie Lavigne | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
JL-002 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Jamie Lavigne | Support | Provide Signature 7 sample / sub footage | Low | In Progress | 50% | 2026-05-10 | 2026-06-20 |  |  | Sample available for The Seals & Prism | Share footage with Chadwick | Open Project

## Steve Griffith
Steve Griffith — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
SG-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Steve Griffith | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
SG-002 | P4-7 | 4 – Portfolio Brand Strategy | Rebuild validation and franchisee confidence within MilliCare | Steve Griffith | Owner | Rebuild validation & franchisee confidence within MilliCare | High | In Progress | 20% | 2026-05-10 | 2026-09-30 |  | Franchisee sentiment low; validation inconsistent | Mapping current validators | Build validator readiness plan | Open Project

## Matt Motyka
Matt Motyka — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
MM-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Matt Motyka | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
MM-002 | P4-6 | 4 – Portfolio Brand Strategy | Utilize Clintar as a selective strategic growth vehicle | Matt Motyka | Owner | Position Clintar as a selective strategic growth vehicle | Medium | In Progress | 30% | 2026-05-10 | 2026-08-15 |  |  | Defining target operator profile | Draft selective growth criteria | Open Project

## Alvaro Leal
Alvaro Leal — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
AL-001 | P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Alvaro Leal | Contributor | Video Coordination with Madsen Anderson | High | In Progress | 30% | 2026-05-15 | 2026-06-20 |  |  | Coordinating with Chadwick | Align on shot list | Open Project
AL-002 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Alvaro Leal | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project
AL-003 | P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Alvaro Leal | Owner | Video Project (Signature 7 – 1-Tom) | High | Complete | 100% | 2026-05-01 | 2026-05-20 |  |  | Complete | Hand off final cut to library | Open Project

## Cassidy Ford
Cassidy Ford — 1:1 Task Tracker
INPUT LAYER · Update your tasks here. Pick a Project ID and the grey columns auto-fill; these tasks roll up to Projects and the Dashboard automatically.
Task ID | Project ID | Focus Area | Tactic / Project Name | Assigned To | Role | Task Description | Priority | Status | Percent Complete | Start Date | Due Date | Dependency | Roadblock | Last Update | Next Step | Hyperlink to Project Sheet
CF-001 | P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Cassidy Ford | Contributor | Training Section 1-3 in Fran Dev 101 | Medium | In Progress | 50% | 2026-05-20 | 2026-06-13 |  |  | Assigned 5/20 | Complete sections 2-3 | Open Project

## Transition Plan (CEO+COO) (hidden)
CEO & COO Transition Plan
Timing: | Oct. 25' to Dec. 25'. Internal announcement December week 3 or 4. External announcement January 1, 2026.
Objectives: | CEO, Ken Hutcheson and COO, Justin Ghadery, collaborate for healthy transition to: 1) stabilize execution, 2) promote adoption, & 3) avoid distractions
Parties Involved: | Justin Ghadery, Ken Hutcheson, & Mike Eblin
Focus Area | Specific Actions | Frequency | Duration
|  | (How often to check-in) | (Date to Reassess)
Advisory Partnership | Executive Coach - Advise new CEO on development areas (strengths & gaps) in various areas of leadership & technical competencies. | Weekly / Bi-Weekly | 12 Months +
| People - Provide feedback to successor on talent ratings for existing people moves, new hires, and potential acquisition needs. Provide input on budgeting process for full year, 4+8, or 6+6 in regard to talent needs. | Ongoing | 12 Months
| Process - Join meetings across brands or at the ESB leadership level when input is needed. | Ongoing | 12 Months
| Performance - Assist with completing MOR and BOD meeting materials. Review performance trends to identify gaps, anticipate trends, and recommend solutions. | Ongoing | 12 Months
ESB Key Priorities & Decisions | Acquisitions - Advise on pre & post close diligence and decisions such as employee needs, development, and revenue opportunities. | Ongoing | 12 Months
| Financial Modeling & Analysis - Assist in monthly MRP review and analysis, MOR & BOD prep, ramp models for existing and new brands for new franchise owners, and marketing fund performance. | Monthly | 12 Months
| Talent - Assist successor in interviews as needed or requested, provide input at EOY review process, and general strategies for talent needs such as upgrades, new positions, or role changes. | Monthly | 3 Months
| Operations - Support national account strategy for all brands including key target customers, pilot programs for expansions such as Relay Fire and Kitchen Guard, and financial management activities for new and existing franchise owners such as business plans, cash management, and other key decisions for new franchise owners. | Monthly | 3 Months
| Support During Crisis Management - Serve as an immediate resource to successor as problems arise with daily operations whether it be team members, franchisee relations, key suppliers, or top customers. | Weekly | 12 Months
Maintain Stakeholder Relationships | “Bridge” the Past, Present & Future - Attend ESB monthly townhalls at discretion of the successor to celebrate past and present accomplishments, while outlining insights for future potential at ESB. | Monthly | 12 Months
| Suppliers & Top Customers - Participate in communication between top vendors and top customer accounts across brands at the request of the successor to signal stability and confidence in sustaining current company performance and relationships, as well as innovating or exploring new areas of the business. | Ongoing | 12 Months
| Foster Collaboration and Trust - Serve as and extension of the successor by sharing information directly or confidentially we you learn of any risk or exposure to the business, as well as team members at flight risk. Continue to advocate for the successor and encourage team members, franchise owners, suppliers, and customers to trust the direction of the portfolio and offer a direct connection to the successor as necessary. | Ongoing | 12 Months
Feedback Loops | Leverage Institutional Knowledge - Advise successor on historical information related to US Lawns company operations as well as B2B industry specific trends of the past, present, and future. | Monthly | 12 Months
| Strategic Initiatives - Review strategic initiatives for ESB and each brand at successor's discretion for specific feedback and opportunities while focusing on a competitive analysis across each of our current companies, expanded service lines across our various companies, and industry specific events to position the brand(s) for best exit value. | Monthly | 12 Months
| Personal Development Plan - Provide successor with regular assessment of performance, both objectively and subjectively, and advise on areas of improvement. | Bi-Weekly | 12 Months
| Guide Leadership Development - Provide input to successor as it relates to ESB management team, brand leaders, and senior leaders across ESB, with specific examples of strengths, areas of improvement, and activities for development in an objective manner. | Monthly | 3 Months

## Lists
ProjectID | Focus Area | Project / Tactic Name | Executive Owner | Strategic Goal (why) | Timing | Orig Status | Lead Owner | StatusList | PriorityList | RoleList
P1-1 | 1 – Unified Development System | Implement standardized Mutual Evaluation Process (MEP) across all brands | Dobelbower | Current franchise development processes vary significantly by brand, creating inconsistent candidate experiences and reducing scalability. | Short (90) | G | Developers | Not Started | Critical | Owner
P1-2 | 1 – Unified Development System | Standardize pipeline stages, definitions, and reporting in CRM | Dobelbower | Inconsistent pipeline definitions and reporting currently limit forecasting accuracy and portfolio-level visibility. | Short (90) | G | Mattingly/Ruhlig | In Progress | High | Contributor
P1-3 | 1 – Unified Development System | Implement DAP (Development Action Plan) timelines for all candidates | Dobelbower | Current candidate progression lacks consistent timelines and accountability, creating unnecessary delays and reduced closing certainty. | Short (90) | G | Developers | Waiting on Someone | Medium | Support
P1-4 | 1 – Unified Development System | Standardize MTTD structure (confirmation event, not sales event) | Dobelbower | MTTD execution varies significantly by brand and should function as a confirmation milestone rather than a late-stage persuasion event. | Mid (180) | na | Developers | Blocked | Low
P1-5 | 1 – Unified Development System | Standardize lead qualification across brands (Lumin, SDR, etc.) | Dobelbower | Qualification standards currently vary by brand, resulting in inconsistent lead quality and inefficient developer utilization. | Short (90) | na | Mattingly/Ruhlig | Complete
P1-6 | 1 – Unified Development System | Launch weekly portfolio-wide pipeline call (eliminate silos) | Dobelbower | Weekly Pipeline Review kicked off 5/5 | Short (90) | C | Developers
P2-1 | 2 – Top-of-Funnel Lead Gen | Centralize non-broker marketing under Chadwick | Dobelbower | Non-broker lead generation efforts are currently fragmented across brands and lack centralized strategic prioritzation. | Short (90) | C | Chadwick
P2-2 | 2 – Top-of-Funnel Lead Gen | Reallocate spend toward non-broker sourced channels | Dobelbower | Marketing spend allocation is not consistently aligned with lead quality, conversion performance, or long-term scalability objectives. | Short (90) | na | Thoma/Chadwick
P2-3 | 2 – Top-of-Funnel Lead Gen | Build video-first funnel | Dobelbower | Video and automation create an opportunity to improve candidate education, consistency, and developer scalability across all brands. | Short (90) | G | M. Anderson/Leal
P2-4 | 2 – Top-of-Funnel Lead Gen | Establish portfolio-level KPIs benchmarked against AFDR ratios | Dobelbower | Portfolio-level KPIs are necessary to properly evaluate marketing efficiency, lead quality, and channel performance across brands. | Mid (180) | na | Mattingly
P2-5 | 2 – Top-of-Funnel Lead Gen | Eliminate low-quality lead sources | Dobelbower | Certain lead sources currently produce volume without corresponding conversion performance or franchisee quality. | Short (90) | na | Chadwick
P3-1 | 3 – Broker Channel | Assign MaryFran as broker channel owner | Dobelbower | Broker relationships currently lack centralized ownership and consistent management across the portfolio. | Short (90) | C | MF. Anderson
P3-2 | 3 – Broker Channel | Route 100% of broker leads through CRM for centralized intake and visibility. | Dobelbower | Shared inboxes and inconsistent lead routing create missed opportunities and limited visibility into broker activity. | Short (90) | G | Mattingly
P3-3 | 3 – Broker Channel | Implement rules-based lead distribution | Dobelbower | Lead distribution should prioritize fairness, responsiveness, and performance while eliminating perception of uneven opportunity. | Short (90) | na | Mattingly/Ruhlig
P3-4 | 3 – Broker Channel | Enforce speed-to-lead SLAs | Dobelbower | Response speed remains one of the largest drivers of broker lead conversion and candidate engagement. | Short (90) | na | MF. Anderson
P3-5 | 3 – Broker Channel | Segment Brokers into Tier 1/Tier 2/ Tier 3 | Dobelbower | Not all broker relationships generate equal value, requiring prioritization based on production and lead quality. |  | na | MF. Anderson
P3-6 | 3 – Broker Channel | Introduce performance-based lead weighting | Dobelbower | Lead distribution should reward execution and conversion performance while maintaining equitable opportunity across the team. |  | na | Mattingly/Ruhlig
P3-7 | 3 – Broker Channel | Build weekly broker channel performance reporting | Dobelbower | Broker performance visibility is currently limited, making it difficult to optimize relationships and conversion performance. | Short (90) | na | Mattingly/Ruhlig
P4-1 | 4 – Portfolio Brand Strategy | Position The Seals as a low-cost, high-whitespace growth brand | Dobelbower | The Seals presents an opportunity for accelerated unit growth due to low investment requirements, recurring revenue characteristics, and significant whitespace availability. | Short (90) | G | Anderson/Chadwick
P4-2 | 4 – Portfolio Brand Strategy | Position 1-Tom as a flagship growth brand | Dobelbower | 1-Tom possesses strong branding, broad market appeal, and favorable long-term scalability characteristics. | Short (90) | G | Anderson/Chadwick
P4-3 | 4 – Portfolio Brand Strategy | Align Kitchen Guard growth strategy with Strategic Accounts initiatives | Dobelbower | Kitchen Guard’s compliance-driven recurring revenue model aligns well with enterprise and Strategic Account positioning opportunities. | Long (270) | G | Hatcher
P4-4 | 4 – Portfolio Brand Strategy | Reposition Prism as a multi-service platform opportunity | Dobelbower | Prism’s multi-service structure creates an opportunity to increase average deal size and long-term franchisee value. | Short (90) | G | Anderson/Chadwick
P4-5 | 4 – Portfolio Brand Strategy | Maintain stable, quality-focused growth for U.S. Lawns | Dobelbower | U.S. Lawns serves as a mature and stable portfolio brand with strong recognition and operational consistency. | Short (90) | G | Steeves
P4-6 | 4 – Portfolio Brand Strategy | Utilize Clintar as a selective strategic growth vehicle | Dobelbower | Clintar should be positioned toward experienced operators and strategic opportunities rather than high-volume franchise sales efforts. | Mid (180) | G | Motyka
P4-7 | 4 – Portfolio Brand Strategy | Rebuild validation and franchisee confidence within MilliCare | Dobelbower | Long-term MilliCare growth requires improvement in franchisee sentiment, validation consistency, and economic confidence. | Long (270) | na | Griffith/Weaver
P5-1 | 5 – Operational Infrastructure | Replace shared territory check inboxes with CRM routing | Dobelbower | Shared territory check workflows currently create operational inefficiencies and inconsistent response times. | Short (90) | na | Mattingly
P5-2 | 5 – Operational Infrastructure | Implement territory check response SLA | Dobelbower | Fast and consistent response times are critical to broker experience and franchise sales momentum. | Short (90) | G | MF. Anderson
P5-3 | 5 – Operational Infrastructure | Standardize lead assignment and routing logic | Dobelbower | Lead routing should prioritize transparency, accountability, and operational consistency across brands. | Short (90) | na | Mattingly
P5-4 | 5 – Operational Infrastructure | Build centralized KPI dashboard and reporting visibility | Dobelbower | Leadership currently lacks consistent portfolio-wide visibility into funnel health and conversion trends. | Mid (180) | na | Mattingly/Ruhlig
P5-5 | 5 – Operational Infrastructure | Improve CRM adoption and reporting discipline | Dobelbower/Mattingly | Consistent CRM usage is required to improve forecasting accuracy and operational visibility. | Short (90) | G | Developers
P6-1 | 6 – Automation & Content | Develop standardized brand overview videos | Dobelbower | Standardized brand messaging improves candidate consistency and reduces repetitive developer workload. | Mid (180) | G | M Anderson/Leal
P6-2 | 6 – Automation & Content | Develop validation preparation and candidate education content | N/A | Better-prepared candidates improve validation outcomes and increase overall process efficiency. | Short (90) | G | Dobelbower
P6-3 | 6 – Automation & Content | Create standardized FDD and process walkthrough videos | Dobelbower | Automation of repetitive educational content increases scalability and developer capacity. | Short (90) | na | M Anderson/Leal
P6-4 | 6 – Automation & Content | Build centralized content library across brands | Dobelbower | Centralized content infrastructure improves consistency and speed of deployment across the portfolio. | Long (270) | G | M Anderson/Leal
P6-5 | 6 – Automation & Content | Automate early-stage candidate education | Dobelbower | Automation creates operational leverage while improving consistency of the candidate experience. | Mid (180) | G | Mattingly/Ruhlig
P7-1 | 7 – Operating Rhythm | Implement weekly KPI scorecards by brand, developer, and source | Dobelbower | Transparent performance reporting improves visibility and operational decision-making. | Mid (180) | G | Mattingly
P7-2 | 7 – Operating Rhythm | Conduct monthly funnel conversion and marketing reviews | Dobelbower | Regular conversion analysis is necessary to optimize marketing efficiency and franchise development performance. | Short (90) | G | Chadwick/MF Anderson
P7-3 | 7 – Operating Rhythm | Standardize forecasting methodology | Dobelbower | Forecasting methodologies currently vary across brands, limiting portfolio-level planning and visibility. | Short (90) | G | Mattingly
P7-4 | 7 – Operating Rhythm | Establish clear initiative ownership and accountability | N/A | Consistent ownership structures are required to improve execution discipline and cross-functional alignment. | Short (90) | G | Dobelbower
P8-1 | 8 – Talent Evaluation | Evaluate the current Franchise Development team to identify top performers, growth opportunities, and long-term leadership potential. | N/A | This assessment will help ensure the organization has the right talent structure in place to support scalable growth across all brands. | Short (90) | G | Dobelbower
P8-2 | 8 – Talent Evaluation | Establish standardized performance expectations and KPI accountability across all Franchise Development roles. | N/A | Creating consistent scorecards and benchmarks will improve visibility, alignment, and operational discipline throughout the department. | Short (90) | G | Dobelbower
P8-3 | 8 – Talent Evaluation | Identify capability gaps and organizational needs across recruiting, sales execution, broker management, and lead conversion. | N/A | Understanding where additional support, training, or restructuring is needed will strengthen overall development effectiveness. | Short (90) | G | Dobelbower
P8-4 | 8 – Talent Evaluation | Build a long-term talent development strategy focused on coaching, succession planning, and cross-brand collaboration. | N/A | Investing in team development will create a more scalable and sustainable franchise development organization over time. | Short (90) | G | Dobelbower